## Sheet1
Sprint | Task | Description | Total Hours
Sprint 1 | User Registration | Create a user registration form with validation. | 5
| Validate Input | Ensure all fields are validated before submission. | 2
| Confirmation Email | Send confirmation email upon successful registration. | 3
| Login Functionality | Create login form | 3
| Logout Functionality | Implement logout feature | 3
| Password Reset | Create a password reset functionality | 4
| Email Verification | Implement email verification after registration | 3
23
Sprint 2 | View Products | Display available products | 5
| Filter Products | Allow filtering by categories and price ranges | 4
| Sort Products | Implement sorting options (e.g., price, popularity) | 3
| Search Product | Implement search functionality for products | 4
12
Sprint 3 | Product Detail Page | Create a product page with images and descriptions | 5
| Related Products | Show related products on product detail page | 3
| Add to Cart | Implement "Add to Cart" functionality | 4
| View Reviews | Display user reviews for products | 3
18
Sprint 4 | Shopping Cart Management | Develop a cart page to view and modify cart items | 5
| Update Cart Items | Allow users to update item quantities in the cart | 3
| Remove From Cart | Implement functionality to remove items from the cart | 3
| Checkout Process | Create a multi-step checkout process | 6
15
Sprint 5 | Payment Gateway | Integrate payment gateway | 8
| Payment Method Selection | Allow users to choose a payment method | 3
| Order Confirmation | Implement order confirmation page | 3
| Track Order | Develop functionality for users to track their orders | 4
22
Sprint 6 | Admin Panel | Create an admin panel for managing products, orders, and users | 8
| User List | View a list of registered users with search and filter options | 4
| Manage Products | Add, edit, delete products | 10
| Manage Categories | Create, edit, or delete product categories | 4
| View Order Details | Display detailed information of each order | 5
| Update Order Status | Change the status of orders (e.g., processing, shipped) | 4
| Refund Management | Process refunds for customer orders | 3
| Reports | Generate reports on sales and purchase history | 7
| Manage Payment Options | Configure available payment methods (e.g., credit card, PayPal) | 4
| Admin Notifications | Set up notifications for important admin actions | 3
| User Activity Logs | Track user activities for security purposes | 4
| Bulk Actions | Enable bulk actions for product and order management | 5
31
|  | TOTAL ESTIMATED HOURS FOR FOUR TEAM MEMBERS IN TWO WEEKS | 121
NOTE:
2 WEEKS
4 TEAM MEMBERS